## Slide 1: Romanian - Norwegian Strategic Cooperation in Maritime Higher Education for enhancement human capital and knowledge base in field of marine intelligent technologies
MARINTECH

## Slide 2
ROMANIAN NAVAL ACADEMY 1st Fulgerului Street, Constanta, România, 900218 Tel/ Fax: +40-241-643096 Email erasmus@anmb.ro
MARINETECH - Romanian - Norwegian Strategic Cooperation in Maritime Higher Education for enhancement human capital and knowledge base in field of marine intelligent technologies Constanta, Romania, 21.09-24.09.2021

## Slide 3: Information
Project no: 20-COP-66 /14.02.2021
Project start date: 01 Sep 2021
Project end date: 31 Aug 2023
Applicant institution: Academia Navala „ Mircea cel Bătrân”
Partner: Norges teknisk-naturvitenskapelige universitet / NTNU i Ålesund
TOTAL BUDGET: 162393,00 EUR
  MBNA – 65440 EUR
  NTNU – 96953 EUR
Funded under the EEA Grants- Financial Mechanism 2014-2021
THE EDUCATION, SCHOLARSHIPS, APPRENTICESHIPS AND YOUTH ENTREPRENEURSHIP PROGRAMME (ESAYEP), 2014-2021

## Slide 4: Project activities
A. PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
O. INTELLECTUAL OUTPUTS/ACTIVITIES
M. MULTIPLIER EVENTS
C. LEARNING/TEACHING/TRAINING ACTIVITIES

## Slide 5: A. PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
A1-M1 – the first month of the project - date of the signature of the contract – September 2021
A2- M8 – Aprilie 2022
A3 – M12 - August 2022
A4 – M19 - March 2023
A5 – M24 - August 2023
Budget:
  MBNA – 12000 EUR
  NTNU – 6000 EUR + Transnational project meeting * 2 persons = 848 (indiv.support) +720 (travel ) = 1568 Eur

## Slide 6: A. PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
TPM Transnational project management meetings

## Slide 7: O. INTELLECTUAL OUTPUTS/ACTIVITIES
Budget:
  O1: MBNA – 12210 EUR
  O1: NTNU – 39765 EUR
  O2: MBNA – 9410 EUR
  O2: NTNU – 14460 EUR
  O5: MBNA – 1480 EUR
  O2: NTNU – 4820 EUR
  O1 – M1 September 2021 – M12 August 2022
  O2 – M1 September 2021 – M23 July 2023
  O5 – M1 September 2021 – M24 August 2023

## Slide 8: O. INTELLECTUAL OUTPUTS/ACTIVITIES

## Slide 9: O. INTELLECTUAL OUTPUTS/ACTIVITIES
O1
NTNU - "Practical applications in marine robotics" -28 hours/semester (course-14 hours + laboratory-14 hours)-2 ECTS;
MBNA - "Applications of intelligent technologies in bathymetry and oceanography"-28 hours/semester (course-14 hours + laboratory-14 hours)-2 ECTS;
NTNU - "Machine learning applications in maritime industry" -28 hours/semester (course-14 hours + laboratory-14 hours)-2 ECTS.

## Slide 10: O. INTELLECTUAL OUTPUTS/ACTIVITIES
O2
1 virtual advanced distributed learning platform for sharing the course content to the students for specific courses developed in O1 (course materials, video-tutorial, digital resources);
1 virtual collaborative e-campus for teachers and researchers, where the academics to be connected peer-to-peer with their colleagues in the partner campuses, by forum dialogue, sharing the teaching practices results in the marine intelligent technologies area of knowledge;
1 virtual e-section dedicated to promote the infrastructure facilities where each partner will be able to provide information about the own didactic infrastructure and the conditions under which laboratories and infrastructure could be available for interested persons/researching groups, among the partners.

## Slide 11: O. INTELLECTUAL OUTPUTS/ACTIVITIES
O3
2 joint articles to peer-reviewed journals and by setting up a dedicated project webpage to be used as sharing point among the partner's scientists.

## Slide 12
M. MULTIPLIER EVENTS
NTNU - M1 – M13 September 27, 2022
MBNA – M2 – M13 September 29, 2022
NTNU – M3 – M23 July 25, 2023
MBNA – M4 – M23 September 27, 2023
Budget:
  M1: NTNU – 2000 EUR (20 participants*100Eur)
  M2: MBNA – 2000 EUR (20 participants*100Eur)
  M3: NTNU – 2000 EUR (20 participants*100Eur)
  M4: MBNA – 2000 EUR (20 participants*100Eur)

## Slide 13
M. MULTIPLIER EVENTS

## Slide 14
C. LEARNING/TEACHING/TRAINING ACTIVITIES
NTNU - C1 – M10 June, 2022
MBNA – C2 – M9 May, 2022
NTNU – C3 – M20 May, 2023
MBNA – C4 – M21 June, 2023
Budget:
  C1: NTNU – 3700+1800 EUR = 5510 EUR (5 staff)
  C2: MBNA – 3700+1800 EUR = 5510 EUR (5 staff)
  C3: NTNU – 4060+3600= 7660 EUR(10 students) C4: MBNA – 4060+3600= 7660 EUR(10 students)

## Slide 15
C. LEARNING/TEACHING/TRAINING ACTIVITIES
Student_IP | Students participating in Intensive Programmes
STMS | Short term mobility of students

## Slide 16
C. LEARNING/TEACHING/TRAINING ACTIVITIES
STTE | Short term joint staff training events
HEI's_Staff_IP | HEI's staff participating in Intensive Programmes

## Slide 17
C. LEARNING/TEACHING/TRAINING ACTIVITIES
NTNU – C5 – M13 September, 2022
MBNA – C6 – M 23 July, 2022
Budget:
  C5: NTNU – 3700+1800 EUR = 5510 EUR (5 staff)
  – 4060+3600= 7660 EUR(10 students)
  C6: MBNA – 3700+1800 EUR = 5510 EUR (5 staff)
  – 4060+3600= 7660 EUR(10 students)