## Slide 1: SEA MENTORS
KA220 - Cooperation Partnerships in Vocational Education and Training
2021-1-RO01-KA220-VET-000029622
SEAfarers Experiential Knowledge Based MENTORS

## Slide 2: PROJECT OUTLINES
Project Acronym: SEA MENTORS
Project Start Date: 2022-02-01
Project Total Duration: 24 months
Project End Date: 2024-01-31
Grant approved: 184,810 Euro

## Slide 3: Project Partners
RNA - Romanian Naval Academy - Academia Navala "Mircea cel Batran" (E10093117 - Romania)
NVNA - Bulgarian Naval Academy - “Nikola Yonkov Vaptsarov” Naval Academy (E10108590 - Bulgaria)
PNA - Polish Naval Academy - AKADEMIA MARYNARKI WOJENNEJ (E10090628 - Poland)
LMA - Lithuanian Maritime Academy - Lietuvos aukstoji jureivystes mokykla (E10108901 - Lithuania)
MI – Maritime Innovators (E10050928 - Turkey)
SPINAKER Co (Slovenia)

## Slide 4: Project Objectives
SEA MENTORS project will create a platform for seafarers career development at sea and ashore by sharing experiential knowledge for the benefit of such training. It will provide tool for users to interact without having to meet face-to-face or for that matter without even having to be available at the same time;
Building an online joint platform for students counselling and mentoring in carrier path;
Awareness of seafaring cadets regarding the experience onboard the military and civilian ships;
Facilitate the cadets’ insertion onboard military and civilian ships.

## Slide 5
SeaMentors Steering Committee:
Project director: Cătălin Popa
Project responsible PNA: Artur Bogdanowicz
Project responsible LMA: Rima Mickiene
Project responsible NVNA: Ivo Jocov
Project responsible MI: Ugurcan Acar
Project responsible RNA: Filip Nistor
Project responsible Spinaker: Tomaž Gregorič

## Slide 6
Romanian Naval Academy (RNA) |  | 
Name | email address | Responsabilities
Catalin Popa | catalin.popa@anmb.ro | Project director
Nistor Filip | filip.nistor@anmb.ro | Project responsible MBNA
Nicolae Florin | florin.nicolae@anmb.ro | Project implementation expert
Alexandru Cotorcea | alexandru.cotorcea@anmb.ro | Project implementation expert
Cojocaru Carmen | Carmen.cojocaru@anmb.ro | Project implementation expert
Serban Sergiu | Sergiu.serban@anmb.ro | Project implementation expert
Andrei Bautu | andrei.bautu@anmb.ro | Project implementation expert
Marius Cucu | marius.cucu@anmb.ro | Erasmus+ admin officer
Maritime Innovators (MI)/SPINAKER Co |  | 
Name | email address | Responsabilities
Ugurcan Acar | acarugurcan@gmail.com | Project responsible MI
Tomaž Gregorič | tomaz.gregoric@spinaker.si | Project implementation expert
 |  | Project implementation expert
Polish Naval Academy (PNA) |  | 
Name | email address | Responsabilities
Artur Bogdanowicz | a.bogdanowicz@amw.gdynia.pl | Project responsible PNA
Marcin Kluczyk | m.kluczyk@amw.gdynia.pl | Instructor
Andrzej Grządziela | a.grzadziela@amw.gdynia.pl | Instructor
Paweł Wirkowski | p.wirkowski@amw.gdynia.pl | Instructor
Marcin Zacharewicz | m.zacharewicz@amw.gdynia.pl | Instructor
Iwona Królikowska | i.królikowska@amw.gdynia.pl | Instructor
Adam Polak | a.polak@amw.gdynia.pl | Instructor
Radosław Kiciński | r.kicinski@amw.gdynia.pl | Instructor
Piotr Zwolan | p.zwolan@amw.gdynia.pl | Instructor
PhD Sławomir Świerczyński | s.swierczynski@amw.gdynia.pl | Instructor
Łukasz Marchel | l.marchel@amw.gdynia.pl | Instructor
Arkadiusz Adamczyk | a.adamczyk@amw.gdynia.pl | Instructor
Joanna Szczepankowska | j.szczepankowska@amw.gdynia.pl | Administrative Expert
Lithuanian Maritime Academy (LMA) |  | 
Name | email address | Responsabilities
Rima Mickiene | r.mickiene@lajm.lt | Project responsible LMA
Kęstutis Žalys | k.zalys@lajm.lt | Project implementation expert
Indrė Diksė | i.dikse@lajm.lt | Project implementation expert
Vilma Locaitiene | v.locaitiene@lajm.lt | Project implementation expert
Sigita Švanienė | s.svaniene@lajm.lt | Project implementation expert
Working teams
Bulgarian Naval Academy (NVNA) |  | 
Name | email address | Responsabilities
Ivo Yotsov | ivo.yotsov@nvna.eu | Project responsible NVNA
George Dimitrov | g.dimitrov@nvna.eu | Project implementation expert
Nedko Dimotrov | n.dimitrov@nvna.ru | Project implementation expert
Desislava Zografova | erasmus@nvna.eu | Erasmus+ admin officer
Grafiela Staneva | g.staneva@nvna.eu | Accountant
Kalin Kalinov | k.kalinov@nvna.eu | Expert
Georgi Panayotov | g.panayotov@nvna.eu | Expert
Ivan Tsonev | i.tsonev@nvna.eu | Expert
Dilian Dimitranov | d.dimitranov@nvna.eu | Expert
Lachezar Konakov | l.konakov@nvna.eu | Expert
Sevdalin Daskalov | s.daskalov@nvna.eu | Expert
Valentin Zlatev | v.zlatev@nvna.eu | Expert
Svilen Velinov | s.velinov@nvna.eu | Expert
Georgi Gilev | g.gilev@nvna.eu | Expert
Ivailo Bakalov | bakalov@nvna.eu | Expert
Delian Hristov | d.hristov@nvna.eu | Expert
Yordan Sivkov | j.sivkov@nvna.eu | Expert
Yavor Dechev | dechco@naval-acad.bg | technician

## Slide 7: Intellectual outputs

## Slide 8: Intellectual Output 1: SEA MENTOR Training Platform
SEA MENTORS online Training Platform will be designed for seafarers so that they will be able to enhance their experiential knowledge and progress in their career further.
The Training platform will make reference to informal/experience based knowledge and will refer to a common framework that learners have gone through in their training, based on the real experiences.
The platform that will be developed will integrate examples of Mentors past experiences.
These experiential knowledge databank will be transformed and adapted making references to actual rules and regulations set by the administrations.
The training platform will be used by mariners of all ranks can upgrade their skills and be proactive while performing their tasks and making a decisions throughout their personal development.
Universities/Maritime Education and Training centers will become aware of a new and comprehensive understanding of how to transfer experiential knowledge to their students. The Training platform will also be able to prepare the participants to embark upon a sustained process of self-directed skills development and thus in a position to share and develop these competences with colleagues.

## Slide 9: Intellectual Output 1: SEA MENTOR Training Platform
Task 1.1 – Questionnaire for Experiential Knowledge Identification:
A research questionnaire will be developed compiling the questions to the seafarers to identify the best practices in passing the experiential knowledge from one to another in a systematic way. The questionnaire will seek the view of the target groups on the deficiencies in the transfer of experiential knowledge as well as to identify problem areas in maritime context.
The question subject will cover Mentoring, Mentor Teachers, Cadetship Promotion, Coaching, Soft Skills Development, Interview in job market and Cultural Aspects. This questionnaire will be sent to all project target groups. A report will be produced based on the outcome of the results.
Each partner will review the method of delivery in the implementation of "experiential knowledge" transfer and best practices in their country. Interviews with experienced seafarers (mentors) will beconducted to support the findings of questionnaire. Led by MBNA

## Slide 10
Task 1.2. Platform specifications and methodology: Specifications and a methodology both functional and technical will be discussed, agreed and documented prior development of the tool presenting experiential based knowledge gathered through Mentors. Led by MARITIME INNOVATORS
Task 1.3. Content development: It will be based on the "experiential knowledge" collected through consultation from the potential mentors. It will cover Captains, 1st Officers, Officers, Chief Engineers, 1st Engineers in both Merchant and Royal Navy. The content will cover Mentoring, Mentor Teachers, Cadetship Promotion, Coaching, Soft Skills Development; Interview in job market, Cultural Aspects. Results collated through questionnaire/interviews will be used in putting together the final content. Led by NVNA
Task 1.4. Programming of online platform: A technological solution as a web-based platform using an advanced learning platform. The latter will be an advanced platform with capabilities for course creation, configuration and packaging to standardised formats, learning communities’ creation and management, both synchronous and asynchronous learning, collaboration and evaluation services, etc. Interactive simulations of identified scenarios of critical situations or any other type of learning content will be plugged in the learning platform and used by the learners. The platform is offered by Spinaker to the project. Led by SPINAKER

## Slide 11
Task 1.5. Design User Interface: The partners will agree on n User Interface that is most suitable for the training which will give easy access and allows for self-explaining interaction. The course will function through a popular Graphical User Interface, a user-centred design that shall be user-friendly, simple, easy to use. Led by PNA
Task 1.6. Testing and Improving: In line with EQAVET principles the partners will evaluate and improve the e-learning system developed. This will lead receiving approval from industrial and social partners. 3 piloting groups will be separately arranged after the improvements have taken place. 3 piloting groups will be formed with at least 8 seafarers/end-users from the 3 different countries (Poland, Lithuania, Romania) with an experienced teacher. A teacher will lead the group and verify their knowledge and fill their knowledge gaps. All participants including the teacher will fill in a questionnaire. All questionnaires will be summarised into one report and improvements made.

## Slide 12: Intellectual Output 2: SEA MENTOR Guidance Tool
This IO offering technological solution will allow online access to the advanced Online "Experiential Knowledge" Guidance tool.
The tool will be designed to provide new users new skills and knowledge acquired from Sea Mentors Online Platform - the tool will have the the capability to store, retrieve, manipulate and present meaningful information extracted from experiential knowledge.
Main product of the intellectual output will be an on line tool to be used by seafarers to learn experiential knowledge presented in the platform so that lessons can be learned from past experiences.
It will be used by juniors interested in progressing to further ranks such as captain/engineers (mentors) which will help them enhance their competence via learning from others and create better opportunities to work.
The tool will provide a platform for juniors a choice of additional career paths, including entrepreneurship.
This guidance tool may be used at all levels and open to captains additional pathways for transition to work. The tools` methodology will include a variety of randomly offered "experiential knowledge databank" for users to access.
On-line tool that will consist from a test, asking questions about the personal interests, personality features, skills, physical condition, knowledge and experience of the user and will provide a feedback with a report suggesting one or more of the experiential knowledge and related Mentors and if requested their profiles.

## Slide 13: Intellectual Output 2: SEA MENTOR Guidance Tool
Task 2.1. Specifications and methodology: The specifications and methodology for the tool will be discussed and agreed between partners that will subsequently formulate "experiential knowledge" database for the tool. Based on the outcome, the IT partner will develop an example which will be discussed and reviewed to move next stage. Once the specifications and methodologies have been developed, tested and approved against the Total Quality Management Plan, a short handbook will be produced to be used by the partners involved in the software development. Led by SPINAKER
Task 2.2. On-line tool development: The tool will be packaged in standardised forms with various sections concerning a particular level of depth in knowledge, skills and understanding for a given level of seniority, and concerning a given job function. It will be specifically designed for informal learning based for those who work at sea and study ashore for navigational/engineering capacity besides formal learning. The on-line guidance tool will be fully parametrical to allow transfer, changes and adaptation. Results will be multilingual in all partners’ languages, including English which is the international language for merchant marine. SPINAKER will have the responsibility of the development considering the outputs of IO1 and IO2. Led SPINAKER with support from MARITIME INNOVATORS

## Slide 14
Task 2.3. Programming the tool: The partners will together agree the parameters of this tool, which include easy access and reliability. One important reliability indicator of this tool is its high level of rotation of data so that even if the user repeats the test, the probability of having the same information will be minimal. Led by SPINAKER
Task 2.4. Design User Interface: A User Interface will be agreed by the partners that is most suitable for the tool, gives easy access and allows for self-explaining interaction of the user with the tool by visualising all interactions, and smartly supporting the variety of media used in learning while keeping the user’s attention and motivation during test time. Led by NVNA
Task 2.5. Testing and finalising: A piloting plan will be developed based on industry standard procedures relating to the testing of online web based applications undertaken and signed off by SPINAKER. The plan will also include guidelines for usability testing to be undertaken by all partners, selection of students and seafarers from the partner organisations. The partners will test the tool in house. For that purpose they will set up in line with EQAVET a testing plan, divide the tasks between themselves, collate the testing results and act on the improvements required. Feedbacks collected will be analysed and be used for final improvement by IT partners. Led by PNA

## Slide 15: Project Outputs
Web platform- (A21): A project website will provide information about the project and its aims, the partners, the products and results. It will also have an e-newsletter facility where users and subscriber can download and receive up to date versions as they are published. Led by SPINAKER
Press releases-(A13): The press releases will be drafted by all partners, and translated to each partner language under the leadership of MARITIME INNOVATORS. 5 press releases in 6 months interval will be developed during the course of the project. These press releases will be sent to local, national and international magazine, newspapers and other media representatives in all partner countries. NVNA with support from partners.
Newsletters-(A14): The newsletters will be written in rotating order, one by each partner and will be translated by each partner and then distributed by email and on the Web Platform to the partners networks and to stakeholders from all Target Groups. Led By PNA
Dissemination Materials -(A15): The consortium will create a corporate image for the project to secure maximum distribution of the project. This corporate image will be visible in its logo, notepads, pens and flyers that will be distributed from the start of the project to all target groups and stakeholders. MBNA will be in charge of organising these dissemination materials.

## Slide 16
Project Flyer-(A18): These Flyers will be available from the beginning of the project to give a quick overview over the projects aims and objectives and will be widely distributed to all stakeholders and target groups in the partner countries in order to widely spread the awareness of the project and to receives as much input and feedback as possible. Led by SPINAKER
Final Brochure-(A16): Partners will produce a multi-language brochure towards the end of the project, which will be of high quality and will summarise the projects aims, objectives and achievements, introduce the Intellectual Outputs and invite all stakeholders to the use SEA MENTORS Online Platform. Led by MBNA with support from SPINAKER
Tutorial Video-(A19): a short informative video will be compiled towards the end of the project when the both the SEA MENTORS platform been fully tested and improved if necessary, that will explain and demonstrate how to use both products. The video will be uploaded onto the projects Web Platform as well as YouTube. Led by SPINAKER.
Conference papers: Papers will be produced which are directly linked to “Experiential Knowledge Based MENTORING” and studies carried out by the project partners in order to identify the need for project activities. These papers will be aimed at reputable conferences in the maritime industry to inform the target groups on an academic level. Led By MARITIME INNOVATORS with support from all partners

## Slide 17: Intangible Outputs
There will also be several intangible results upon completion of the project such as:
Learning About Culture: Seafarers will exchange enormous number of knowledge and experience through the platform and lead a more rigid maritime culture hence improve the safety of operations at sea. This will lead o the framework of transnationalism by advancing the notion of emporium, in which the circular and transversal journeys of seafarers are viewed as a connecting space between land‐ based areas; a space which provides a basis for an extended knowledge and understanding of different cultural outlooks as well as relations between nations.
Safety Culture at sea: Recognising that all accidents are preventable and normally only occur following unsafe actions or a failure to follow correct procedures thereby thinking safety constantly will be encouraged in the platform.

## Slide 18: Project IMPACT
The partnership embraces the impact on participants, participating organisations, target groups and other relevant stakeholders that the project will:
Enhance and advance competence for Seafarers through transfer of experiential knowledge transfer from seniors to juniors at sea. With the facility to use this anywhere and anytime, the autonomous experience share mode is expected to have immediate impact for those mariners competence.
The education and training providers as well as the authorities will be provided with a ready-made experiential knowledge based platform offered in 5 languages enabling them to introduce it directly into their existing training programmes, meaning that there will be a direct and immediate impact on the vocational training in the maritime sector that have been hidden as informal learning
The educational services of the partners involved in the development of the product, will benefit and will be further developed by the partners for their in house training.
It is expected that the intended course will lead to recognition by major accrediting and licensing bodies in partner countries. This will add impact and credibility to the tools produced by the project. There is a genuine interest in making maritime professions in Europe more attractive to young people and thus improving the employment of seafarers.

## Slide 19: Events and transnational meetings

## Slide 20: TRANSNATIONAL MEETINGS
TM1 Project Management-Kick-off Meeting”, two days organizational meeting, organized by the Romanian Naval Academy in Romania in (29th -30th March 2022)
TM2 working meeting, organized by the Lithuanian Maritime Academy in Lithuania (07th -08th November 2022)
TM3 working meeting, to be organized by the Polish Naval Academy in Poland in M13 (27th -29th March 2023)
TM4 working meeting, to be organized by the SPINAKER Company in Slovenia in M17 (27th -29th March 2023)
TM5 final meeting, to be organized by the Romanian Naval Academy in Romania (October 2023)
EVENTS
“Final Conference”, 1 day event, 60 national and 10 international participants, to be organized by the ”Mircea cel Batran” Naval Academy in Romania in M19 (17th of November 2023)

## Slide 21
RNA will organize in Constanta, the TM1 Kick off Meeeting gathering the 2 members of each partner in M3.
RNA will organize in Constanta, the E1 for 60 local and 10 international participants in M20.
RNA will be Task leader for O1.
RNA Responsabilities

## Slide 22
MI will assure the management guidance for the partners in IO1 and IO2.
MI will responsible for IO2.
Maritime Innovators Responsabilities

## Slide 23
LMA will organize in Constanta, the TM2 gathering the 2 members of each partner in M9.
LMA will participate in implementation of O1 and IO2.
LMA Responsabilities

## Slide 24
PNA will organize in Gdynia, the TM3 M13.
PNA will participate in implementation of O1 and IO2.
PNA Responsabilities

## Slide 25
NVNA will participate in implementation of IO1 and IO2.
NVNA Responsabilities

## Slide 26
Will support the platform development IO2.
SPINAKER Responsabilities

## Slide 27
Teams nomination and working groups per each partner for IO1 / IO2;
Produce 1 roll-up/partner institution (see the model on the marplat.eu);
Post the project logo on the institutional page of the partners;
Use the www.marplat.eu to enrol the team members;
Maritime Innovators – management plan, comm plan, quality management plan;
SPINAKER to produce the project website;
Project management plan is available on the portal and will be updated systematically;
The partners will seek to produce articles for SeaConf – SEAMENTORS worskshop.
RNA will provide the standardise forms for events, courses, TM, financial matters;
Making a directory for posting the future invitations for different events.
Tasks to follow up!

## Slide 28: Discussions? Questions?