## KA2_SP_TIMELINE_TEMPLATE (hidden)
Name of the project: | Development of Common Curricula Modules for Merchant Marine Officers - DECOMAR
PROJECT TIMETABLE
| MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Project activity*
A1 preparation
A2 meetingsO9/A1
A2 meetingsO9/A2
A2 meetingsO9/A3
A2 meetingsO9/A4
A3 dissemination
A4 reports
O1/A1
O1/A2
O2/A1
O2/A2
O3/A1
O3/A2
O4/A1
O4/A2
O5/A1
O5/A2
O6/A1
O6/A2
O7/A1
O7/A2
O8/A1
O8/A2
O8/A3
O8/A4
O9/A1
O9/A2
O9/A3
O9/A4
O10/A1
O11/A1
O11/A2
M1
M2
M3
M4
E1
E2
E3
E4
C1
C2
C3
C4
C5
C6
Please insert rows as needed
*Project activity types:
| An | - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On/An | - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn | - TRANSNATIONAL PROJECT MEETINGS
| En | - MULTIPLIER EVENTS
| Cn | - LEARNING/TEACHING/TRAINING ACTIVITIES
| n | - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.

## Time Line
SEAMENTORS
PROJECT TIMETABLE
No | Intelectual Output | Responsible partner | Duration | Deliverable type | Year | 2022 | [11 empty] | 2023
[5 empty] | Month |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
[6 empty] | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Noi | Dec | Ian
Intellectual Outputs
IO1 | IO 1 SEA MENTOR Training Platform | PRU | 20 months | bar: M1 Feb to 2023 M21 Oct
IO2 | IO 2 SEA MENTOR Guidance Tool | PNA | 15 months | bar: M9 Oct to 2023 M23 Dec
Multiplier events
E1 | Multiplier Event - Final Conference | MBNA | 1 day | 30+10 participants | bar: 2023 M22 Noi
Transnational meetings
M1 | Project Management-Kick-off Meeting - Romania | RNA | 2 days/12pax |  |  | M2 Mar: 29.03
M2 | 2TM - Working meeting - Lithuania | LMA | 2 days/12pax |  |  | M10 Nov: 7-8.11
M3 | 3TM - Working meeting - Poland | PNA | 2 days/12pax |  |  | 2023 M14 Mar: 27-29.03
M4 | 4TM - Working Meeting Slovenia | SL | 2 days/12pax | bar: 2023 M20 Sept
M5 | 5TM - Resuming project results - Romania | RNA | 2 days/12pax |  |  | 2023 M22 Noi: 17.11
Project management | [6 empty] | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24