## TIMELINE_OF ACTIVITIES
Cooperation projects in Higher Education Area
[6 empty] | Financed by EEA Grants 2014-2021 | [14 empty] | F-SEE-011/02,2018
Name of the project: Romanian - Norwegian Strategic Cooperation in Maritime Higher Education for enhancement human capital and knowledge base in field of marine intelligent technologies (MARINTECH)
PROJECT TIMETABLE
|  | Sep | Oct | Noie | Dec | Ian | Febr | Mar | Apr | Mai | Iun | Iul | Aug | Sep | Oct | Noie | Dec | Ian | Febr | Mar | Apr | Mai | Iun | Iul | Aug
| MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
Project activity*
A. PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
A1. Project management meeting, implementation plan | bar: Sep
A2. Online meeting: Joint mobilities, virtual platform and Course module on marine intelligent technologies: „Intellegent technologies application in the maritime industry” | bar: Apr
A3. Online meeting: course module on marine exploitation and organizational Summer school and workshop details | bar: Aug
A4. Online meeting: organizational Summer school and jount mobility details | bar: Mar
A5. Online meeting: Closure meeting | bar: Aug
O. INTELLECTUAL OUTPUTS/ACTIVITIES
O1. “Innovative common curricula for course module on marine intelligent technologies: „Intelligent Technologies Applications in maritime industry" | bar: Sep to Aug
O2. “Virtual training platform on robotics and marine intelligent technologies”
O5: "Dissemination: joint research papers"
M. MULTIPLIER EVENTS
M1. Workshop on: “Cooperation and partnerships between education and labor market on marine intelligent technologies in the North Sea area” | bar: Sep
M2. Workshop on: “Cooperation and partnerships between education and labor market on marine intelligent technologies in the Black Sea area” | bar: Sep
M3. Workshop on: “MARINTECH contribution on enhancing the human capital and knowledge versus the current labour market demands in the North Sea area” | bar: Iul
M4. Workshop on: “MARINTECH contribution on enhancing the human capital and knowledge versus the current labour market demands in the Blach Sea area” | bar: Iul
C. LEARNING/TEACHING/TRAINING ACTIVITIES
C1. “joint staff training events“ - DS | bar: Iun
C2. “joint staff training events“ - BS | bar: Mai
C3. “Joint mobilities for students“ | bar: Apr
C4. “Joint mobilities for students“ | bar: Mai
C5. “Joint Summer School on innovative methods in teaching, learning and evaluation applied in robotics and machine learning from maritime industry” | bar: Sep
C6. “Joint Summer School on innovative methods in teaching, learning and evaluation applied in modern bathymetry and oceanography ” | bar: Iul
Please insert rows as needed
*Project activity types:
| An | Sep: - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On | Sep: - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn | Sep: - MULTIPLIER EVENTS
| Cn | Sep: - LEARNING/TEACHING/TRAINING ACTIVITIES
| n | Sep: - number of the activity
Please enter all main project activities, intellectual outputs, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc.

## buget detaliat
Planning working hours /budget- MARINTECH project
PROJECT TIMETABLE
| Ani | 2021 |  |  |  |  | 2022 | [12 empty] | 2023 | [8 empty] | Total buget/ore
| MONTHS | M1 | M2 | M3 | M4 | Total | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | Total | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | Total
|  | Sep | Oct | Nov | Dec |  | Ian | Feb | Mar | Apr | Mai | Iun | Iul | Aug | Sep | Oct | Nov | Dec |  | Ian | Feb | Mar | Apr | Mai | Iun | Iul | Aug
Activitati finantate
A. PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES (24 luni x 500E) = 12OOO E |  | 500 | 500 | 500 | 500 | 2000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 4000 | 12000
O. INTELLECTUAL OUTPUTS/ACTIVITIES
O1. “Innovative common curricula for course module on marine intelligent technologies: „Intelligent Technologies Applications in maritime industry" (165 zile x 74E)= 12210 E | Month Budget (Euro) | 1036 | 1036 | 1036 | 1036 | 4144 | 1036 | 1036 | 1036 | 1036 | 1036 | 1036 | 1036 | 814 | 0 | 0 | 0 | 0 | 8066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12210
| Teacher hours | 14 | 14 | 14 | 14 | 56 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 11 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165
O2. “Virtual training platform on robotics and marine intelligent technologies” (90 zile x74 E +50 ore *55 E) = 6660E+2750E=9410 E | Month Budget (Euro) | 296 | 296 | 296 | 296 | 1184 | 296 | 516 | 516 | 516 | 516 | 960 | 1256 | 1294 | 1146 | 110 | 110 | 110 | 7346 | 110 | 110 | 110 | 110 | 165 | 165 | 110 | 0 | 880 | 9410
| Days | 4 | 4 | 4 | 4 | 16 | 4 | 4 | 4 | 4 | 4 | 10 | 14 | 16 | 14 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
| Technician hours | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 34 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 0 | 16 | 50
| Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 296 | 296 | 296 | 296 | 0 | 0 | 0 | 1480 | 1480
| Nr. de zile | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 20 | 20
M. MULTIPLIER EVENTS
M2. Workshop on: “Cooperation and partnerships between education and labor market on marine intelligent technologies in the Black Sea area” (20 invitati x 100 E)=2000E | Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
M4. Workshop on: “MARINTECH contribution on enhancing the human capital and knowledge versus the current labour market demands in the Blach Sea area” (20 pers x 100 E)=2000 E | Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000
C. LEARNING/TEACHING/TRAINING ACTIVITIES
C1. “joint staff training events“ - DS (5 prof x1102 E) = 5510E | Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510 | 0 | 0 | 0 | 0 | 0 | 0 | 5510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510
C3. “Joint mobilities forstudents“ (10 stud x 766E) = 7660 E | Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7760 | 0 | 0 | 0 | 7760 | 7760
C5. “Joint Summer School on innovative methods in teaching, learning and evaluation applied in robotics and machine learning from maritime industry” ( 5 prof x 1102E + 10 stud x 766 E) = 5510 E+ 7660E = 13170 E | Buget lunar(Euro) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13170 | 0 | 0 | 0 | 13170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13170
Total buget /an |  | 1832 | 1832 | 1832 | 1832 | 7328 | 1832 | 2052 | 2052 | 2052 | 2052 | 8006 | 2792 | 2608 | 16816 | 610 | 610 | 610 | 42092 | 906 | 906 | 906 | 906 | 8721 | 665 | 610 | 2500 | 16120 | 65540