## Slide 1
MAR-Lang
Linguistic Diversity in European Maritime Higher Education Institutions
TM1
2 February 2023
KA220-HED – Cooperation partnership in higher education

## Slide 2: CONTEXT
Project acronym MAR-LANG
Project starting date 01/12/2022
Project total duration 24 months
Project end date 30/11/2024
Grant lump sum €250,000
Budget Items Allocated amount (EUR)
Work package n°1 Project Management €49,840.00
Work package n°2 - French-English Maritime Terminology collection €95,200.00
Work package n°3 - Virtual Campus Platform €51,549.00
Work package n°4 - Learning, teaching activities €53,411.00
Total 250,000.00

## Slide 3
PARTNERS
École nationale supérieure maritime, Le Havre, France
Mircea cel Batran Naval Academy, Constanta, Romania
Lietuvos aukstoji jureivystes mokykla, Klaipeda, Lithuania

## Slide 4: MAR-Lang STEERING COMMITTEE
Project coordinator: Gersende Le Dimna
Project manager ENSM: Christelle Nicolas
Project manager MBNA: Catalin Popa
Project manager LMA: Rima Mickiene

## Slide 5: TEAMS (Partner 1)
ENSM
Gersende Le Dimna, project coordinator and Head of International Relations and Academic Partnerships gersende.ledimna@supmaritme.fr
Christelle Nicolas, project manager and lecturer in Maritime English christelle.nicolas@supmaritime.fr
Edward Melaert, lecturer in English edward.melaert@supmaritime,fr
Marie Livet, lecturer in Nautical Sciences, Human and Social Sciences and Construction and Safety/Security marie.livet@supmaritime.fr
Pascale Hauret, Administrative and Financial Support pascale.hauret@supmaritime.fr

## Slide 6: TEAMS (Partner 2)
MBNA
Assoc.Prof. Dr. Catalin POPA – catalin.popa@anmb.ro (+407443646632);
LtCdr Marius CUCU - marius.cucu@anmb.ro (+40770115681);
Assoc.Prof. Dr. Sergiu LUPU – sergiu.lupu@anmb.ro (+40744123925);
Assoc.Prof. Dr. Alexandru COTORCEA – alexandru.cotorcea@anmb.ro (+40764440723);
Assoc.Prof. Dr. Filip NISTOR – filip.nistor@anmb.ro (+40723575535);
Prof.Assistant Dr. Andrei POCORA – andrei.pocora@anmb.ro (+40740255018);
Lecturer Dr. Rita AVRAM – rita.avram@anmb.ro (+40742943393);
Lecturer Dr. Corina SANDIUC – corina.sandiuc@anmb.ro (+40720010652);
Lecturer Dr. Camelia ALIBEC – camelia.alibec@anmb.ro (+40723317243);
Lecturer Dr. Edith KAITER – edith.kaiter@anmb.ro (+40724231938);
Lecturer Dr. Raluca APOSTOL MATEȘ – raluca.apostol@anmb.ro (+40723136522);
Assoc.Prof. Dr. Andrei BĂUTU – andrei.bautu@anmb.ro (+40723224504);
IT Eng. Anca ATODIRESEI – anca.atodiresei@anmb.ro (+40723381387).

## Slide 7: TEAMS (Partner 3)
LMA
1. Vilma Pranckeviciute,Lecturer in Maritime English v.pranckeviciute@lajm.lt
2. Dr. Maria Ververi, Lecturer in Maritime English m.ververi@lajm.lt
3. Tatjana Lysenko, International Relations Specialist t.lysenko@lajm.lt
4. Vytautas Jocaitis, IT Administrator v.jocaitis@lajm.lt
5. Rima Mickienė, Project Manager r.mickiene@lajm.lt

## Slide 8: OBJECTIVES
Building a strong cooperative partnership
Building and sharing common curricula for teaching FEM
Increasing the quality of practice and learning of FEM
Opening to new actors
MAR Lang

## Slide 9: PROJECT DESCRIPTION
Development of a web-based digital platform
Virtual Campus Platform (MARPLAT)
Creation of new, innovative and joint curricula or courses
To meet the learning needs of the partner MHEI’s students
Teaching and learning of foreign languages
To reinforce internationalisation and mobility

## Slide 10: 4 WORK PACKAGES
Work package 1: Project Management (24 months)
Work package 2: FEMT Collection (12 months)
Work package 3: Virtual Campus Platform (24 months)
Work package 4: Learning and Teaching Activities (17 months)

## Slide 11: FRENCH-ENGLISH MARITIME TERMINOLOGY COLLECTION
Bilingual glossary of maritime terms in FR and ENG
Curriculum of FR-ENG maritime terminology on
Ship and Cargo Handling course
Naval Engineering course
Port and Maritime Logistics sector course
FR-ENG maritime modules on
Ship and Cargo Handling
Naval Engineering
Port and Maritime Logistics sector

## Slide 12: VIRTUAL CAMPUS PLATFORM
Virtual campus platform: MARPLAT for teachers, students, researchers, professionals and stakeholders
Digital support of the courses: sharing didactic materials, video tutorials among the partner
Four transnational meetings (France, Romania, online)

## Slide 13: LEARNING, TEACHING ACTIVITIES
3 joint training events for teachers
3 joint training events for students
3 public events

## Slide 14: GANTT

## Slide 15: TASKS ALLOCATION
ENSM
Project coordinator
Task leader WP1
Task leader WP2: FEMT collection for Ship and Cargo Handling, Naval Engineering, Port and Maritime Logistics sector. Development of linguistic courses for students
Organisation of three TMs: M3 in LH, M18 online, M23 in Saint-Malo
Organisation in M10 of one TS for 9 lecturers, one TS for 9 students on Ship and Cargo Handling (5 days)
Organisation of one-day public event on FEMT called « FEM Language for Friendship » in M10

## Slide 16: TASKS ALLOCATION
MBNA
Task leader for WP3
Organisation in M6 in Constanta of TM2 – FEM Glossary and Curricula
Organisation in M18 in Constanta of one TS for lecturers and one TS for students on FEMT on Port and Maritime Logistics sector
Organisation in M18 of one-day public event « Crossing maritime linguistic barriers »

## Slide 17: TASKS ALLOCATION
LMA
Task leader WP4 from M5 to M23
Organisation in M23 of one-day public event on FEMT « French for friendship at sea »
Organisation in M12 of one-day online TM3 on Learning resources digitalisation
Organisation in M23 in Klaipeda of one TS for lecturers and one TS for students on FEMT in Naval Engineering

## Slide 18
Discussions?
Questions?