## Slide 1: MARitime Soft Skills for Onboard Healthy Nutrition and CULinary Arts in Seagoing Services – CUL-MAR-Skills Update – 19.02.2025
KA220-VET - Cooperation partnerships in vocational education and training
2023-1-RO01-KA220-VET-000156711
Disclaimer: “Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or the ANPCDEFP. Neither the European Union nor the ANPCDEFP can be held responsible for them”

## Slide 2: PROJECT OUTLINES
Project Acronym: CUL-MAR-SKILL
Project Start Date: 01 of DECEMBER 2023
Project Total Duration: 24 months
Project End Date: 30th of November 2025
Grant approved: 250,000 Euro
Organisation | WP | Budget | Total budget
RNA | 1 | 12600 | 58330
 | 2 | 14670 | 
 | 3 | 15500 | 
 | 4 | 15560 | 
PRU | 1 | 8400 | 56660
 | 2 | 17900 | 
 | 3 | 9300 | 
 | 4 | 21060 | 
UAEGEAN | 1 | 8400 | 52910
 | 2 | 9900 | 
 | 3 | 19050 | 
 | 4 | 15560 | 
NVNA | 1 | 8400 | 52460
 | 2 | 16100 | 
 | 3 | 16900 | 
 | 4 | 11060 | 
CPMR | 1 | 8400 | 29640
 | 2 | 8090 | 
 | 3 | 8650 | 
 | 4 | 4500 | 
TOTAL |  |  | 250000

## Slide 3
C: RNA – Romanian Naval Academy - Academia Navala "Mircea cel Batran" (E10093117 - Romania)
P1: PRU – Piri Reis University - T. C. Piri Reis Universitesi (E10105404 - Turkye)
P2: UAEGEAN – Aegean University - PANEPISTIMIO AIGAIOU- (E10208624 - Greece)
P2: NVNA – Bulgarian Naval Academy - “Nikola Y. Vaptsarov” Naval Academy (E10108590 - Bulgaria)
CRPM – CONFERENCE DES REGIONS PERIPHERIQUES MARITIMES D EUROPE (E10266207 – France)
Cul-Mar-Skills
Steering Committee:
Project director: Col. Cătălin POPA
Coordinator UAEGEAN: Prof. Maria Lekakou
Coordinator CPRF: Stavros Kalognomos
Coordinator PRU: Prof. Taner ALBAYRAK
Coordinator RNA: Lt.Cdr. Marius CUCU
PROJECT ADMINISTRATOR:
Lt.Cdr. Marius CUCU
PROJECT PARTNERS
Coordinator NVNA: Capt. Ivo Yotsov

## Slide 4
Romanian Naval Academy (RNA) |  | 
Name | email address | Responsabilities
Catalin Popa | catalin.popa@anmb.ro | Project director
Marius Cucu | marius.cucu@anmb.ro | Project responsible RNA
Andrei Bautu | andrei.bautu@anmb.ro | Academic staff
Nistor Filip | filip.nistor@anmb.ro | Academic staff
Atodiresei Dinu | dinu.atodiresei@anmb.ro | Academic staff
Lupu Sergiu | sergiu.lupu@anmb.ro | Academic staff
Bulgarian Naval Academy (NVNA) |  | 
Name | email address | Responsabilities
Ivo Yotsov | ivo.yotsov@nvna.eu | Project responsible NVNA
Magdalena A. Stefanova | ma.stefanova@naval-acad.bg | Administrative expert (accountant)
Teodora Dragomirova Gandeva | t.gandeva@nvna.eu | Administrative expert (Erasmus+ admin officer)
Yoanna Staneva-Tsvetkova | erasmus@nvna.eu | Administrative expert (Erasmus+ admin officer)
Kalin Kalinov | k.kalinov@nvna.eu | Academic staff
Evgenya Krizhanovska | e.krizhanovska@nvna.eu | Academic staff
Kamelya Narleva | k.narleva@nvna.eu | Academic staff
Petya A. Atanasova | atanasova.p@nvna.eu | Academic staff
Nikola Dukov | n.dukov@nvna.eu | Academic staff
Zhaneta Kalinova | zh.kalinova@nvna.eu | Academic staff
PiriReis University(PRU) |  | 
Name | email address | Responsabilities
Taner Albayrak | t.albayrak@pirireis.edu.tr | Project responsible PNA
Pinar Ozdemir | p.ozdemir@pirireis.edu.tr | Academic staff
Ugur Kacan | ukacan@pirireis.edu.tr | Academic staff
Hüseyin GENCER | hgencer@pirireis.edu.tr | Academic staff
EKER İŞÇİOĞLU | teiscioglu@pirireis.edu.tr | Academic staff
Kenan TATA | ktata@pirireis.edu.tr | Academic staff
Working teams
Aegean University(UAEGEAN) |  | 
Name | email address | Responsabilities
Maria Lekakou | mlek@aegean.gr | Project responsible
Bountziouka Vasiliki | vboun@fns.aegean.gr | Academic staff
Katsounis Ioannis | ykatsounis@stt.aegean.gr | Academic staff
Georgios Georgoulis | g.georg@aegean.gr | Academic staff
Iakovaki Eleni | e.iakovaki@aegean.gr | Academic staff
Papazi Katerina | K.Papazi@aegean.gr | Administrative officer
CPRM |  | 
Name | email address | Responsabilities
Stavros Kalognomos | Stavros.Kalognomos@crpm.org | Project responsible CRPM
Maria Tersmette | Maria.Tersmette@crpm.org | Communication expert
Emmanuel Maniscalco | emmanuel.maniscalco@crpm.org | Administrative expert
Sylvia Langlais | sylvia.langlais@crpm.org | Administrative officer

## Slide 5
Work packages - brief description:
Work package n°1 – ” Project Management” (42 600 Euro) – responsible partner: Romanian Naval Academy, period: 01.12.2023-30.11.2025;
Work package n°2 - „”Onboard Healthy Nutrition” - specialized training module for seafaring personnel” (66 660 Euro) – responsible partner: Romanian Naval Academy, period: 01.01.2024-31.12.2024;
Work package n°3 – ” Training programs for professional skills in victualling logistic services and seafaring food procurement” (69 400 Euro) – responsible partner: Bulgarian Naval Academy, period: 01.03.2024-31.05.2025;
Work package n°4 – ” Maritime Culinary Arts Training Module” (67 740 Euro) – responsible partner: PiriReis University, period: 01.07.2024-30.09.2025.

## Slide 6
Major foreseen results:
→ 1 research survey and 1 follow up report (done);
→ 5 training modules (1 WP2, 3 WP3, 1 WP4):
  „Onboard Healthy Nutrition” (WP2) - (by December 2024) to be included in intermediary report!!!;
  „Supply Chain Management and the Victualling Services Onboard ” (WP3) (by 01st of May 2025);
  „Entrepreneurial Opportunities in Seagoing Procurement Services ” (WP3) (by 01st of May 2025);
  „Sustainable Development and the Green Transition to Effective Galleys Services Onboard the Ships ” (WP3) (by 01st of May 2025);
  „Onboard Cook Skills” (WP4) (by 30th of September 2025);
→ 1 Cook Manual for Seafaring Cuisine Services Onboard the Ships (by 30th of September 2025);
→ 5 transnational meetings;
→ 3 events.

## Slide 7
Project budget allocated for work packages:

## Slide 8
Project time line – Gantt chart:

## Slide 9
Work package n°1 description – coordinator Romanian Naval Academy
→ Romanian Naval Academy as coordinator will be responsible for Project Management Plan elaboration and implementation and the Steering Committee will be the authority to command and control all aspects of the PMP.
→ PMP includes the following plans:
Human resource management plan (HRMP), Self - Evaluation Management Plan (SEMP),
Quality management plan (QMP), Schedule management plan (SMP), Monitoring management Plan (MMP),
Dissemination and exploitation plan (DEP),
Communications management plan (CMP),
Risk management plan (RMP).

## Slide 10
ADMINISTRATIVE ARRANGEMENTS
15th of December 2023 – contract have been signed – done!;
31st of December 2023 – budget have been transfered to the partners 1st installment: 40% of the total;
30th of November 2024 – intermediary report submission!!!;
30th of November 2024 – progress report (supporting documents to be provided) – load the time sheets according to the budget lines!!!;
31st of December 2024, after IR approval – budget to be transfered to the partners 2nd installment: 40% of the total budget;
30th of November 2025 – final report submission;
After final report approval – final 20% of the budget will be transfered to the partners.
The administrative forms are uploaded on following folder: https://marplat.eu/course/view.php?id=63
WP1 – TASKS AND RESPONSABILITIES:

## Slide 11
Work package n°2 description – coordinator Romanian Naval Academy (RNA)
”Onboard Healthy Nutrition” - specialized training module for seafaring personnel
A.2.1. Study of Onboard Nutrition - survey and report - RESULTS: Study of nutrition components, feeding behaviour, eating habits; a report for optimum diet variations changing with different factors will be prepared → responsible: PRU;
A2.2. ”Onboard Healthy Nutrition Fundamentals” training module development – RESULTS: A course on "Onboard Healthy Nutrition” will be prepared by the partners as training module (textbox, presentations, on hand materials, practical activities and case studies) → responsible: RNA;
A2.3. Transnational meetings and events – RESULTS:
→ TPM1 Transnational Project: kick-off meeting (RNA, Romania, 2 pax/2 days) period: 17/01/2024 - 20/01/2024 (done!);
→ TPM2 Transnational Project Meeting virtual meeting - ,,Healthy nutrition outlines in seafaring activities – Project progress report” (2 pax/partner/1 day) (RNA, Romania), period: 15th of May 2024 (done!)
E1. Seminar ”Improvement solutions for healthy nutrition in seafaring activities”, RNA, Romania, 43 participants – RESULTS: 1 promoting campaign will be conducted, project results to be presented, feed-back from participants will be collected, period: 16/05/2025 (after C1 will be ready);

## Slide 12
C1T. Training module for instructors "Onboard Healthy Nutrition” – responsabile: RNA, Romania (3 instructors/partner) (in Romania, Constanta) RESULTS: 1 training material to be developed and tested with professional trainers as training module support for "Onboard Healthy Nutrition”, period: 04/11/2024 - 08/11/2024.
COURSES TO BE ORGANIZED during WP2:
Team members nominated for "Onboard Healthy Nutrition"course development:
COURSE | RNA team members | PRU team members | UAEGEAN team members | NVNA team members | CPRM team members
"Onboard Healthy Nutrition" | LtCdor Marius Cucu marius.cucu@anmb.ro | Pinar Ozdemir p.ozdemir@pirireis.edu.tr | Bountziouka Vasiliki vboun@fns.aegean.gr | Kamelya Narleva k.narleva@nvna.eu | 

## Slide 13
Work package n°2 time line – coordinator Romanian Naval Academy (RNA)
No | WORK PACKAGES |  |  | Responsible partner | Duration (Months/Days) | Year | 2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Month | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
 |  |  |  |  |  |  | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov
WP1 - Project management |  | Project management (RNA) |  | RNA | 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A1.1 | Project management |  | RNA | 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 - ”Onboard Healthy Nutrition” - specialized training module for seafaring personnel | A2.1 | Study of Onboard Nutrition - survey and report |  | RNA | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.2 | ”Onboard Healthy Nutrition Fundamentals” training module development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.3 | Project meetings and events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.3.1 | TM1 | Project Kick-off meeting - RNA, Romania – 3 days residential (2 pax/partner) | RNA | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.3.2 | TM2 | Transnational Project Meeting - Healthy nutrition outlines in seafaring activities - Project progress report | VIRTUAL | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.3.3 | Events | E1 - Seminar ”Improvement solutions for healthy nutrition in seafaring activities”, RNA, Romania, 43 participants | RNA | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A2.3.4 | LLT | C1T. Training module for instructors "Onboard Healthy Nutrition" (3 instructors/participant) | RNA | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 14
Work package n°2 budget baseline – coordinator Romanian Naval Academy (RNA)
Work package |  |  |  | Activities | RNA | PRU | UAEGEAN | NVNA | CPMR | Total budget
 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 
WP 1 | A1.1 | Project management |  |  | 12600 | 8400 | 8400 | 8400 | 8400 | 46200
TOTAL WP 1 |  |  |  |  | 12600 | 8400 | 8400 | 8400 | 8400 | 46200
WP2 - ”Onboard Healthy Nutrition” - specialized training module for seafaring personnel | A2.1, A22 | Study of Onboard Nutrition - survey and report |  |  | 10800 | 12600 | 3600 | 10800 | 3600 | 41400
 | A2.2 | Project meetings and events |  |  | 3870 | 5300 | 6300 | 5300 | 4490 | 25260
 | A2.2.1 | TPM1 | Project Kick-off meeting - RNA, Romania – 3 days residential (2 pax/partner) | Project Kick-off meeting - RNA, Romania – 3 days residential (2 pax/partner) | 0 | 2000 | 2400 | 2000 | 2800 | 9200
 | A2.2.2 | TPM2 | Transnational Project Meeting - Healthy nutrition outlines in seafaring activities - Project progress report | Transnational Project Meeting - Healthy nutrition outlines in seafaring activities - Project progress report | 0 | 0 | 0 | 0 | 0 | 0
 | A2.3 | E1 | E1 - Seminar ”Improvement solutions for healthy nutrition in seafaring activities”, RNA, Romania, 43 participants | E1 - Seminar ”Improvement solutions for healthy nutrition in seafaring activities”, RNA, Romania, 43 participants | 3870 | 0 | 0 | 0 | 0 | 3870
 | A2.4 | C1T | C1T. Training module for instructors "Onboard Healthy Nutrition" (3 instructors/participant) | C1T. Training module for instructors "Onboard Healthy Nutrition" (3 instructors/participant) | 0 | 3300 | 3900 | 3300 | 1690 | 12190
 | Total WP2 |  |  |  | 14670 | 17900 | 9900 | 16100 | 8090 | 66660

## Slide 15
TIME LINE for IMPLEMENTATION
December – May 2024 – format design for learning materials (word, ppt, lab);
January – June 2024 – curriculum design (syllabuses approval);
May 2024 – December 2024 – learning materials development (revision on 04-08.11);
January 2025 – April 2025 – platform upload, learning materials roll-on and testing;
April 2024 – October 2024 – module development, testing the materials with the students in learning activities.
ACTIVITIES TO BE ORGANIZED during WP2
TM1 – Kick off meeting – RNA, Constanta, Romania – 3 days, 2 pax/partner, 17-20.01.2024 (done!);
TM2 – Healthy nutrition outlines in seafaring activities – online, RNA, May 2024 – 1 day, 2 pax/partner, 15.05.2024 (done!);
C1T. Training module for instructors "Onboard Healthy Nutrition", RNA, Romania (3 instructors/partner) (RNA, Romania) period: 04.11.2024 – 08.11.2024 (done!);
E1 Public event E1: ”Improvement solutions for healthy nutrition in seafaring activities” – organized by RNA, in Romania – 1 day, 43 participants, (scheduled for SeaConf 2025, 16-17th of May 2025);
WP2 – TASKS AND RESPONSABILITIES:

## Slide 16
WP2 – quantitative results:
The following results are expected to be achieved during the WP2 activities:
→ 1 research survey and 1 follow up report that will include identifying the common dietary patterns and habits among seafarers, assessing the nutritional status and requirements of seafarers, and evaluating the effectiveness of existing nutrition programs and policies on board.
→ 1 training module ”Onboard Healthy Nutrition” and the respective curriculum will be designed, consisting in textbox, power point presentations and training on-hand case studies.
→ 2 transnational meetings - TPM1 will be organized by RNA in Romania and TPM2 will be organized virtually, both meetings having as objective the progress report regarding the A2.1 and A2.2. results, counting 2 participants/partners/TPP, total of 20 participants.
→ 1 course module conducted with trainers - C1T - Training module for instructors "Onboard Healthy Nutrition" organized by RNA in Romania counting 3 attending instructors/partner, in total of 13 participants – 04-08 November 2024.

## Slide 17
Work package n°3 description – coordinator Bulgarian Naval Academy (NVNA)
”Training programs for professional skills in victualling logistic services and seafaring food procurement”
A.3.1. Curriculum analysis and training modules development in Victualling Logistic Services and
Onboard Food Procurement- RESULTS: Curriculum development and 3 training modules content (textbox, presentations, case studies, training on hand exercises) → responsible: NVNA (period 01/03/2024-31/05/2025);
A3.2. Transnational meetings and events – RESULTS:
  → TPM3 Project meeting – virtual project meeting - Curricular developments for Food Logistics Services responsible: RNA, period 19.02.2025;
  → TPM4 Transnational Project Meeting - Curricular developments for Entrepreneurship in Victualling
  Logistics Services, responsible: NVNA, Bulgaria (2 pax/partner), period 12.05.2025-15.05.2025;
E2. Seminar ”Logistics Services in Maritime Agencies and Onboard Feeding Management” → responsible: UEAGEAN, Greece, 35 participants, 09.12.2024! (presentations from the conference to be completed);
E3. Seminar ”Sustainable Development and Entrepreneurship in Maritime Services” → responsible: NVNA, Bulgaria, 35 participants, 14.05.2025.

## Slide 18
SUMMER SCHOOL for Trainers/Trainees:
C2T. ”Summer Training School for Trainers” – responsabile: UEAGEAN, Greece (1 trainer/partner) – responsabile: UEAGEAN, in Greece (1 trainer/partner), RESULTS: Testing the training resources, laying the foundations for an entrepreneurial mindset focused on maritime, especially victualling logistic services: 07.04.2025 – 11.04.2025 (invitation, AF, agenda, settings, details).
C3S. ”Summer Training School for Cadets” – responsabile: UEAGEAN, in Greece (3 trainees/partner), RESULTS: Testing the training resources, laying the foundations for an entrepreneurial mindset focused on maritime, especially victualling logistic services: 07.04.2025 – 11.04.2025 (invitation, AF, agenda, settings, details).
OBJECTIVE: Testing the training resources, laying the foundations for an entrepreneurial mindset focused on maritime, especially victualling logistic services. A „Short term entrepreneurship booklet" will be prepared after the summer school.
COURSES TO BE ORGANIZED during WP3:

## Slide 19
WP3 – quantitative results:
→ As main result of WP3, implemented under NVNA coordination, 3 training modules will be created, consisting in textbox, presentations, training on-hand case studies, as following:
  - "Supply Chain Management and the Victualling Services Onboard" training module - responsible PRU;
  - "Entrepreneurial Opportunities in Seagoing Procurement Services" training module - responsible NVNA;
  - "Sustainable Development and the Green Transition to Effective Galleys Services Onboard the Ships" training module - responsible UAEGEAN.
→ The training materials will consists in textbox, power point presentations and training on-hand case studies, to be prepared for each course. The training material will be designed to be used in distance education too, using the digital resources and virtual campus (marplat.eu), managed by the RNA, the project coordinator.
→ A summer school will be organized for both, trainees and trainers, as a Teaching, Training, Learning Activity.

## Slide 20
Work package n°3 time line – coordinator Bulgarian Naval Academy (NVNA)
No | WORK PACKAGES |  |  | Responsible partner | Duration (Months/Days) | Year | 2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Month | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
 |  |  |  |  |  |  | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov
WP3 - Training programs for professional skills in victualling logistic services and seafaring food procurement | A3.1 | Curriculum analysis and training modules development in Victualling Logistic Services and Onboard Food Procurement |  | NVNA | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A3.2 | Project meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A.3.2.1 | TM3 | Transnational Project Meeting - Curricular developments for Food Logistics Services, VIRTUAL | VIRTUAL | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A.3.2.2 | TM4 | Transnational Project Meeting - Curricular developments forEntrepreunership in Victualling Logistics Services – NVNA, Bulgaria – 3 days residential (2 pax/partner) | NVNA | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A3.3 | Public Events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A3.3.1 | E2 | E2 - Seminar ”Logistics Services in Maritime Agencies and Oboard Feeding Magement” - UEAGEAN, Greece, 35 participants | UAEGEAN | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A3.3.2 | E3 | E3 - Seminar ”Sustainable Development and Entrepreunership in Maritime Services” - NVNA, Bulgaria, 35 participants | NVNA | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A.3.4 | LLT Summer Training School |  | UAEGEAN | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A.3.4.1 | LLT | C2T. Summer Training School for Teachers - Curriculum design and case studies development - UEAGEAN, Greece (1 trainer/partner) | UAEGEAN | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A.3.4.2 | LLT | C3S. Summer Training School for Cadets - UEAGEAN, Greece (3 trainees/partner) | UAEGEAN | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 21
Work package n°3 budget baseline – coordinator Bulgarian Naval Academy (NVNA)
Work package |  |  | Activities | RNA | PRU | UAEGEAN | NVNA | CPMR | Total budget
 |  |  |  | 1 | 2 | 3 | 4 | 5 | 
TOTAL WP 2 |  |  |  | 14670 | 17900 | 9900 | 16100 | 8090 | 66660
WP 3 | A3.1 | Curriculum analysis and training modules development in Victualling Logistic Services and Onboard Food Procurement |  | 9000 | 4500 | 13500 | 9000 | 4500 | 40500
 | A3.2 | Project meetings |  |  |  |  |  |  | 9200
 | A.3.2.1 | TPM3 | Transnational Project Meeting - Curricular developments for Food Logistics Services, VIRTUAL | 0 | 0 | 0 | 0 | 0 | 0
 | A.3.2.2 | TPM4 | Transnational Project Meeting - Curricular developments for Entrepreunership in Victualling Logistics Services – NVNA, Bulgaria – 3 days residential (2 pax/partner) | 2000 | 2000 | 2400 | 0 | 2800 | 9200
 | A3.3 | Public Events |  |  |  |  |  |  | 6300
 | A3.3.1 | E2 | E2 - Seminar ”Logistics Services in Maritime Agencies and Oboard Feeding Magement” - UEAGEAN, Greece, 35 participants | 0 | 0 | 3150 | 0 | 0 | 3150
 | A3.3.2 | E3 | E3 - Seminar ”Sustainable Development and Entrepreunership in Maritime Services” - NVNA, Bulgaria, 35 participants | 0 | 0 | 0 | 3150 | 0 | 3150
 | A.3.4 | LLT Summer Training School |  |  |  |  |  |  | 13400
 | A.3.4.1 | C2T | Summer school Teachers - observers - 1 pax (UEAGEAN) | 1500 | 1300 | 0 | 1600 | 1350 | 5750
 | A.3.4.2 | C3S | Summer school Students - 3 pax (UEAGEAN) | 3000 | 1500 | 0 | 3150 | 0 | 7650
TOTAL WP 3 |  |  |  | 15500 | 9300 | 19050 | 16900 | 8650 | 69400

## Slide 22
TIME LINE for IMPLEMENTATION
May 2024 – December 2024 – curriculum design (syllabuses approval) – 3 courses WP3
December 2024 – April 2025 – learning materials development – 3 courses WP3
April 2025 – May 2025 – platform upload, learning materials roll-on and testing – 3 courses WP3
May 2025 – June 2025 – BIP development, testing the materials with the students in learning activities
ACTIVITIES TO BE ORGANIZED during WP3
TPM3 Project meeting – virtual project meeting - Curricular developments for Food Logistics Services responsible: RNA, period 19.02.2025/13.00;
TPM4 Transnational Project Meeting - Curricular developments for Entrepreneurship in Victualling Logistics Services, responsible: NVNA, Bulgaria (2 pax/partner), period 12.05.2025-15.05.2025;
E2. Seminar ”Logistics Services in Maritime Agencies and Onboard Feeding Management” → responsible: UEAGEAN, Greece, 35 participants, 09.12.2024;
E3. Seminar ”Sustainable Development and Entrepreneurship in Maritime Services” → responsible: NVNA, Bulgaria, 35 participants, 14.05.2025.
WP3 – TASKS AND RESPONSABILITIES:

## Slide 23
Work package n°4 description – coordinator Piri Reis University (PRU)
”Maritime Culinary Arts Training Module”
A.4.1. Developing a training program for seafaring cooks and cook candidates - RESULTS: course catalogue for the lesson and material for the units it covers → responsible: PRU, period: 01.07.2024 – 31.08.2025;
A4.2. Cook Manual for Seafaring Cuisine Services Onboard the Ships – RESULTS: 1 Cook Manual for Seafaring Cuisine Services Onboard the Ships (collection of selected cuisine recipes) → responsible: PRU, period: 01.07.2024 – 31.08.2025;
A4.3. TPM5. Transnational Project Meeting -Seafaring Cooking Booklet → responsible: CPRM, organized in France, 3 days residential (2 pax/partner), period: 25.08.2025 – 29.08.2025;
C4S. Training module for cooking skills → responsible: PRU, organized in Turkye, for 3 cadets/partner, period: 19.05.2025 – 24.05.2025.

## Slide 24
C4S. ”Training module for cooking skills” – responsabile: PRU, in Turkye (3 trainees/partner), RESULTS: training module on cooking cuisine: 19.05.2025 – 24.05.2025.
OBJECTIVE: Digital manual collecting all the activities and course contents will be prepared. Additionally, a cookbook containing popular food cooked on board in the participating countries for centuries will be prepared. This is the most comprehensive result of the project since it addresses not only the training and education of the students but also the maintenance of cultural heritage.
COURSES TO BE ORGANIZED during WP4:

## Slide 25
Work package n°4 time line – coordinator Piri Reis University (PRU)
No | WORK PACKAGES |  |  | Responsible partner | Duration (Months/Days) | Year | 2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Month | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
 |  |  |  |  |  |  | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Ian | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov
WP4 - Maritime Culinary Arts | A4.1 | Developing a training program for seafaring cooks and cook candidates |  | PRU | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A4.2 | Cook Manual for Seafaring Cuisine Services Onboard the Ships |  | PRU | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A4.2 | TM5 | Transnational Project Meeting -Seafaring Cooking Booklet - CPMR, France – 3 days residential (2 pax/partner) | CPMR | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A4.3 | LLT | C4S. Training module for cooking skills, PRU, Turkye (3 cadets/partner) | PRU | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 26
Work package n°4 budget baseline – coordinator Piri Reis University (PRU)
Work package |  |  | Activities |  | RNA | PRU | UAEGEAN | NVNA | CPMR | Total budget
 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 
WP 4 | A4.1, A4.2 | Developing a training program for seafaring cooks and cook candidates |  |  | 9000 | 18000 | 9000 | 4500 | 4500 | 45000
 | A4.2 | TPM5 |  | Transnational Project Meeting -Seafaring Cooking Booklet - CPMR, France – 3 days residential (2 pax/partner) | 3060 | 3060 | 3060 | 3060 | 0 | 12240
 | A4.3 | C4S |  | C4S. Training module for cooking skills, PRU, Turkye (3 cadets/partner) | 3500 | 0 | 3500 | 3500 | 0 | 10500
TOTAL WP 4 |  |  |  |  | 15560 | 21060 | 15560 | 11060 | 4500 | 67740
TOTAL PARTNERS |  |  |  |  | 58330 | 56660 | 52910 | 52460 | 29640 | 250000
TOTAL |  |  |  |  |  |  | 250000 |  |  | 

## Slide 27
TIME LINE for IMPLEMENTATION
June 2024 – September 2024 – curriculum design (syllabuses approval)
September 2024 – April 2025 – learning materials development
April 2025 – July 2025 – platform upload, learning materials roll-on and testing
July 2025 – September 2025 – course development, testing the materials with the students in learning activities
ACTIVITIES TO BE ORGANIZED during WP3
TPM5. Transnational Project Meeting - Seafaring Cooking Booklet → responsible: CPRM, organized in France (Brussels), 3 days residential (2 pax/partner), period: 25.08.2025 – 29.08.2025;
C4S. Training module for cooking skills → responsible: PRU, organized in Turkye, for 3 cadets/partner, period: 19.05.2025 – 24.05.2025.
WP4 – TASKS AND RESPONSABILITIES:

## Slide 28
C1 "Onboard Healthy Nutrition” – responsible partner: RNA/PRU
C2 "Victualling Onboard" - food supply chain management on board (determining, purchasing, storing, preparing, cooking, serving) – responsible partner: PRU
C3 "Entrepreneurial Opportunities in Procurement" – to provide students with an entrepreneurial mindset – responsible partner: NVNA
C4 "Green Transition in Blue Galleys" - to increase the awareness of the students on waste management an environment protection, emphasizing the importance of hygiene-sanitation to prevent diseases on board, on environment-friendly practices – responsible partner: UAEGEAN
C5 "Onboard Cook Skills" – responsible partner: PRU
COURSES TO BE DEVELOPED during WP2/WP3/WP3/WP4
Training programs for professional skills in victualling logistic services and seafaring food procurement

## Slide 29
COURSES TO BE DEVELOPED during WP2/WP3/WP4:
Team members for CUL-MAR-Skills courses’ development:
COURSE | RNA team members | PRU team members | UAEGEAN team members | NVNA team members | CPRM team members
"Onboard Healthy Nutrition" (RNA/PRU) | Sergiu Lupu sergiu.lupu@anmb.ro | Pınar Özdemir TL pozdemir@pirireis.edu.tr | Bountziouka Vasiliki vboun@fns.aegean.gr |  | 
"Supply Chain Management and the Victualling Onboard" (PRU) | Marius Cucu marius.cucu@anmb.ro | Hüseyin Gençer TL hgencer@pirireis.edu.tr |  |  | 
"Entrepreneurial Opportunities in Seagoing Procurement Services„ (NVNA) | Nistor Filip filip.nistor@anmb.ro | Tutku Eker İşçioğlu teiscioglu@pirireis.edu.tr |  | NVNA – team leader | 
"Sustainable Development and the Green Transition to Effective Galleys Services Onboard the Ships" (UAEGEAN) | Atodiresei Dinu dinu.atodiresei@anmb.ro | Uğur Kaçan ukacan@pirireis.edu.tr |  | UAEGEAN – team leader | 
”Onboard Cook Skills” (PRU) | Popa Cătălin catalin.popa@anmb.ro | Taner Albayrak talbayrak@pirireis.edu.tr |  |  | 

## Slide 30
TASK TO FOLLOW!
ADMINISTRATIVE TASKS
Prepare the documents for planned events (invitation, ;
The team members should register themselves on marplat.eu platform (all the partners will make available the nominations and the email addresses of their team members);
PROJECT IMPLEMENTATION - ACADEMIC TASKS
Establish the project teams: team members in the course development groups;
Proposal for own events/courses – each partner should advance a proposal when the event should be organized depending on the institutional agenda;
The partners have agreed upon the course format – each partner will develop the materials under their responsability, and will share the results in the working groups.

## Slide 31
QUESTIONS?
Thank you for your kind attention!