## Slide 1: International Naval Semester Development Applying the Intelligent Technologies and the Innovative Tools in the European Navy Defense System – NAVY-INS-Tech https://www.anmb.ro/navy-ins-tech https://marplat.eu/course/view.php?id=62 Update – 15.02.2024
KA220-HED - Cooperation partnerships in higher education
2023-1-RO01-KA220-HED-000155888

## Slide 2: PROJECT OUTLINES
Project Acronym: NAVY-INS-Tech
Project Start Date: 01 of NOVEMBER
Project Total Duration: 22 months
Project End Date: 2025 SEPTEMBER 1ST
Grant approved: 250,000 Euro
Partners budget split - allocation on workpackage |  |  | 
Organisation | WP | Budget | Total budget
RNA | WP1 | 16800 | 68200
 | WP2 | 24880 | 
 | WP3 | 14540 | 
 | WP4 | 11980 | 
NVNA | WP1 | 8400 | 60700
 | WP2 | 30580 | 
 | WP3 | 13640 | 
 | WP4 | 8080 | 
PNA | WP1 | 8400 | 60300
 | WP2 | 28780 | 
 | WP3 | 14140 | 
 | WP4 | 8980 | 
INA | WP1 | 8400 | 60800
 | WP2 | 28300 | 
 | WP3 | 16300 | 
 | WP4 | 7800 | 

## Slide 3: Project Partners
RNA - Romanian Naval Academy - Academia Navala "Mircea cel Batran" (E10093117 - Romania)
NVNA - Bulgarian Naval Academy - “Nikola Y. Vaptsarov” Naval Academy (E10108590 - Bulgaria)
PNA - Polish Naval Academy - AKADEMIA MARYNARKI WOJENNEJ (E10090628 - Poland)
INA – Italian Naval Academy - Accademia Navale di Livorno (E10265533 - Italy)
NAVY-INS-Tech
Steering Committee:
Project director: Col. Cătălin POPA
Coordinator PNA: Dr. Monika WYSOCKA
Coordinator INA: Cdr. Walter ROMANO
Coordinator NVNA: CAPT (N) Nedko DIMITROV
Coordinator RNA: Lt.Cdr. Ovidiu CRISTEA
PROJECT ADMINISTRATOR:
Lt.Cdr. Marius CUCU
PROJECT PARTNERS

## Slide 4
Romanian Naval Academy (RNA) |  | 
Name | email address | Responsabilities
Catalin Popa | catalin.popa@anmb.ro | Project director
Ovidiu Cristea | ovidiu.cristea@anmb.ro | Project responsible RNA
Marian Ristea | marian.ristea@anmb.ro | Academic staff
Dinu Atodiresei | dinu.atodiresei@anmb.ro | Academic staff
Greti Manea | greti.manea@anmb.ro | Academic staff
Andrei Bautu | andrei.bautu@anmb.ro | Academic staff
Nistor Filip | filip.nistor@anmb.ro | Academic staff
Marius Cucu | marius.cucu@anmb.ro | Erasmus+ admin officer
Polish Naval Academy (PNA) |  | 
Name | email address | Responsabilities
Monika Wysocka | mo.wysocka@amw.gdynia.pl | Project responsible PNA
Radosław Tyślewicz | r.tyslewicz@amw.gdynia.pl | Academic staff
Piotr Bekier | p.bekier@amw.gdynia.pl | Academic staff
Agata Załęska-Fornal | a.fornal@ | Academic staff
Marcin Kluczyk | m.kluczyk@amw.gdynia.pl | Academic staff
Joanna Szczepankowska | j.szczepankowska@amw.gdynia.pl | Administrative officer
Working teams
Italian Naval Academy (LMA) |  | 
Name | email address | Responsabilities
 |  | Project responsible INA
 |  | Academic staff
 |  | Academic staff
 |  | Academic staff
 |  | Academic staff
 |  | Academic staff
 |  | Administrative officer
Bulgarian Naval Academy (NVNA) |  | 
Name | email address | Responsabilities
Nedko Dimitrov | n.dimitrov@nvna.eu | coordinator
Teodora Minkova | teodora t.minkova@naval-acad.bg | finance
Desislava Zografova | d.zografova@nvna.eu | admin
Veselin Atanasov | atanasov@nvna.eu | Researcher "Naval Electronics"
Darin Peev | d.peev@nvna.eu | Researcher "Naval Electronics"
Jelyazko Nikolov | j.nikolov@nvna.eu | Researcher "Naval Communications"
Georgi Markov | g.markov@nvna.eu | Researcher "Computer networks"
Nadezhda Vladimirova | n.vladimirova@nvna.eu | Researcher "Maritime Cyber Threats"
Lyuba Gyurova | l.gyurova@nvna.eu | Researcher "Power plants"
Nedko Dimitrov | n.dimitrov@nvna.eu | Researcher "Naval Sensors"
Ivaylo Mitishev | i.mitishev@naval-acad.bg | Researcher "Oceanography"
Pavel Ivanov | p.ivanov@nvna.eu | Researcher "Naval Architecture"
Valeri Stoyanov | v.stoyanov@nvna.eu | Researcher „Naval Leadership"
Valentin Vasilev | valentin.vasilev@nvna.eu | Researcher „Maritime Security"
Nikola Stoyanov | nikola.stoyanov@nvna.eu | Researcher „Maritime Security"
Siyana Lutzkanova | s.lutzkanova@nvna.eu | Researcher „CSDP"
Stanislava Stefanova | st.stefanova@nvna.eu | Researcher „Navy Perspectives on Gender"

## Slide 5
Major foreseen results:
1 joint harmonized curriculum;
8 STEM courses learning and teaching materials, using modern and intelligent technologies;
4 HASS courses learning and teaching materials, centered on EU culture and values;
8 short term students exchanges to be organized: 4 STEM modules x 16 students = 64 students and 4 HASS modules x 8 students= 16 students, total of 80 students exchanged;
5 transnational meetings to be conducted;
3 public events organized in each partner country, with at least 30 attendees/event;
1 e-campus will be implemented with digital resources avaialble in EMILYO network (www.marplat.eu) by all interested BOEI;
1 International Naval Semester implemented/harmonized learning resources.

## Slide 6
Work packages - brief description:
Work package n°1 – ”Project Management” (42 000 Euro);
Work package n°2 - „Development of a harmonized International Naval Semester curriculum, using the intelligent technologies and innovative tools in NHEI-Navy Military Higher Education Institutions, to enhance the STEM competences” (112 540 Euro);
Work package n°3 – ”Development of a European Security and Defence culture within the International Naval Semester framework, building the social competences in NHEI-Navy Higher Education Institutions” (58 620 Euro);
Work package n°4 – ”Building a teaching NHEI Network to enhance the implementation of the International Naval Semester using the STEM intelligent technologies and innovative tools in Navy Higher Education in harmonization with the HASS European values” (36 840 Euro).

## Slide 7
Project budget allocated for work packages:

## Slide 8
Project time line – Gantt chart:

## Slide 9
Work package n°1 description – coordinator Romanian Naval Academy
→ Romanian Naval Academy as coordinator will be responsible for Project Management Plan elaboration and implementation and the Steering Committee will be the authority to command and control all aspects of the PMP.
→ PMP includes the following plans:
Human resource management plan (HRMP), Self - Evaluation Management Plan (SEMP) – Responsible: Polish Naval Academy,
Quality management plan (QMP), Schedule management plan (SMP), Monitoring management Plan (MMP) – Responsible: Bulgarian Naval Academy,
Dissemination and exploitation plan (DEP), Communications management plan (CMP), Risk management plan (RMP) – Responsible: Italian Naval Academy.

## Slide 10
ADMINISTRATIVE ARRANGEMENT
February 2024 – contract have been signed, except INA – to be concluded latest by 20th of February;
December 2023 – 40% of the budget has been transfered to the partners, except to INA – to be concluded latest by 20th of February;
30th of September 2024 – intermediary report;
September 2024 – 40% of the total budget will be transfered to the partners as 2nd installments, after the intermediate report approval;
Each IG meeting – progress report (supporting documents);
31st of August 2025 – final report;
After final report approval – final 20% of the budget will be transfered to the partners.
WP1 – TASKS AND RESPONSABILITIES:

## Slide 11
Work package n°2 description – coordinator ”Nikola Vaptsarov” Naval Academy (NVNA)
A.2.1. European Navy curricular design for improving STEM skills in Navy Military Higher Education - RESULTS: 1 curriculum in compliance with SQF-MILOF and 8 harmonized syllabuses (8 STEM) → responsible: NVNA;
A2.2. Course design using the modern technologies and innovative tools for improving STEM competencies in Navy Military Higher Education – RESULTS: 8 courses, digital learning packages, consisting in textbox, presentations, exercises and assessment forms → responsible: NVNA;
A2.3/A2.4. Transnational meetings and events – RESULTS: TPM1 Project Kick-off meeting (RNA, 2 days) and TPM2 Project meeting – STEM curriculum design (virtual meeting), Public event E1: SQF-MILOF standards and STEM curriculum priorities in Navy Military Higher Education (RNA, Romania);
A2.5. Train the students abilities in STEM - Learning/Teaching activities (4 students/partner/course):
C1S. STEM harmonized curriculum for digital skills and IT technology abilities - ”Computer Networks” and ”Maritime
Cyber Threats” modules in International Naval Semester (PNA, Poland);
C2S. STEM harmonized curriculum for competencies in Hi Tech, Electronics and Telecommunications - ”Naval Electronics”
and ”Naval Communications” modules in International Naval Semester (NVNA, Bulgaria);
C3S. STEM competencies in Navy Engineering and Intelligent Weapon Systems - ”Power Plants” and ”Naval Sensors” modules in International Naval Semester (INA, Italy);
C4S. STEM competencies in Naval Sciences - ”Oceanography/ METOC” and ”Naval Architecture” modules in International Naval Semester (RNA, Romania).

## Slide 12
Work package n°2 timeline – coordinator ”Nikola Vaptsarov” Naval Academy (NVNA)

## Slide 13
STEM education (SCIENCES, TECHNICAL, ENGINEERING)
Power Plants – coordinator: Italian Naval Academy (3 ECTS)
Naval Sensors – coordinator: Italian Naval Academy (3 ECTS)
Computer network – coordinator: Polish Naval Academy (2 ECTS)
Naval Cyber Threats – coordinator: Polish Naval Academy (2 ECTS)
Naval Electronics – coordinator: Bulgarian Naval Academy (3 ECTS)
Naval Communication – coordinator: Bulgarian Naval Academy (3 ECTS)
Oceanography – coordinator: Romanian Naval Academy (2 ECTS)
Naval Architecture – coordinator: Romanian Naval Academy (3 ECTS)
WP2- Course resources will be harmonized in the project framework – responsible partners:

## Slide 14
Team members for STEM courses’ development:
COURSES | RNA team members | NVNA team members | PNA team members | INA team members
Naval Sensors (INA) | Popa Silviu silviu.popa@anmb.ro | Nedko Dimitrov n.dimitrov@nvna.eu | Piotr Bekier p.bekier@amw.gdynia.pl | 
Power Plants (INA) | Ristea Marian marian.ristea@anmb.ro | Lyuba Gyurova l.gyurova@nvna.eu | Marcin Kluczyk m.kluczyk@amw.gdynia.pl | 
Computer network (PNA) | Băutu Andrei andrei.bautu@anmb.ro | Georgi Markov g.markov@nvna.eu | Jacek Zalewski - Leader j.zalewski@amw.gdynia.pl | 
Naval Electronics (NVNA) | Cristea Ovidiu ovidiu.cristea@anmb.ro | Veselin Atanasov - Leader atanasov@nvna.eu | Michał Przybylski m.przybylski@amwgdynia.pl | 
Naval Communication (NVNA) | Cristea Ovidiu ovidiu.cristea@anmb.ro | Jelyazko Nikolov - Leader j.nikolov@nvna.eu | Artur Szczepański a.szczepański@amw.gdynia.pl | 
Naval Cyber Threats (PNA) | Băutu Andrei andrei.bautu@anmb.ro | Nadezhda Vladimirova n.vladimirova@nvna.eu | Przemysław Rodwald p.rodwald@amw.gynia.pl | 
Oceanography (RNA) | Atodiresei Dinu - Leader dinu.atodiresei@anmb.ro | Ivaylo Mitishev i.mitishev@naval-acad.bg | Czesław Dyrcz c.dyrcz@amw.gdynia.pl | 
Naval Architecture (RNA) | Manea Greti - Leader greti.manea@anmb.ro | Pavel Ivanov p.ivanov@nvna.eu | Waldemar Mironiuk w.mironiuk@amw.gdynia.pl | 

## Slide 15
TIME LINE for IMPLEMENTATION
28th of February 2024 – format design for learning materials (text, ppt, lab) - RNA;
February – April 2024 – curriculum design and syllabuses approval in the working groups;
April 2024 – January 2025 – learning materials development (textbox, ppt, study cases, lab booklet);
January 2025 – June 2025 – platform upload, learning materials roll-on and testing;
April 2024 – November 2024 – BIP development, testing the materials with the students in learning activities.
ACTIVITIES TO BE ORGANIZED during WP2
TM1 – Kick off meeting – RNA, Constanta, Romania, February 2024 – 3 days, 2 pax/partner, 13-16.02.24;
TM2 – STEM curriculum – online, PNA, May 2024 – 1 day, 2 pax/partner, 14.05.2024;
E1 Public event: Public event E1: SQF-MILOF standards and STEM curriculum priorities in Navy Military Higher Education – organized by RNA, in Romania – 1 day, 30 participants, 17th of May 2025;
Online groups meetings for each course organized by the leading team.
WP2 – TASKS AND RESPONSABILITIES:

## Slide 16
COURSES TO BE ORGANIZED during WP2
C1S. STEM harmonized curriculum for digital skills and IT technology abilities – organized by PNA, in Poland - 2 modules to be delivered as BIP:”Computer Networks” (2 ECTS) and ”Maritime Cyber Threats”, online theory, residentially skills (labs, seminars) - 16 students to be instructed (4 students/partner) – 5 days, october TBD;
C2S. STEM harmonized curriculum for competencies in Hi Tech, Electronics and Telecommunications – organized by NVNA, in Bulgaria - 2 modules to be delivered as BIP: ”Naval Electronics” (3 ECTS) and ”Naval Communications” (3ECTS)- online theory, residentially skills (labs, seminars) - 16 students to be instructed (4 students/partner) – 5 days, 24.06-28.06.2024 (confirmed);
C3S. STEM competencies in Navy Engineering and Intelligent Weapon Systems – organized by INA, in Italy - 2 modules to be delivered as BIP: ”Power Plants” (3 ECTS) and ”Naval Sensors”(3 ECTS) - online theory, residentially skills (labs, seminars) - 16 students to be instructed (4 students/partner) – 5 days, 07.10-11.10.2024;
C4S. STEM competencies in Naval Sciences – organized by RNA, in Romania - 2 modules to be delivered as BIP: ”Oceanography” (2 ECTS) and ”Naval Architecture” (3 ECTS) - online theory, residentially skills (labs, seminars) - 16 students to be instructed (4 students/partner) – 5 days, 11.11-15.11.2024 (confirmed).
WP2 – TASKS AND RESPONSABILITIES:

## Slide 17
Work package n°3 description – coordinator Polish Naval Academy (PNA)
A.3.1. Curriculum design for building an European culture and an European Security and Defence awareness to improve the HASS competencies in NMHE - RESULTS: 1 curriculum in compliance with SQF-MILOF) and 4 HASS harmonized syllabuses → responsible: PNA;
A3.2. Curriculum design for building an inclusive European culture and a Security and Defence awareness to improve the HASS competencies in Navy Military Higher Education – RESULTS: 4 courses, digital learning packages, consisting in textbox, presentations, exercises and assessment forms → responsible: PNA;
A3.3. Transnational meetings and events – RESULTS: TPM3 Project meeting – EU core of values curricular developments (NVNA Bulgaria);
A3.4. Train the students abilities in HASS - Learning/Teaching activities (2 students/partner/course) :
C5S. NHEI ESDP harmonized curriculum for developing an EU Security culture CSDP (RNA, Romania);
C6S. NHEI ESDP harmonized curriculum for Maritime Security (NVNA, Bulgaria);
C7S. NHEI ESDP harmonized curriculum for Naval Leadership on EU core values (INA, Italy);
C8S. NHEI EU diversity competencies - Gender Navy Perspectives seminar (PNA, Poland).

## Slide 18
Work package n°3 timeline – coordinator Polish Naval Academy (PNA)

## Slide 19
HASS education (HUMANITIES, SOCIAL SCIENCES and EU culture)
Naval Leadership – coordinator: Italian Naval Academy (2 ECTS)
Maritime Security – coordinator: Bulgarian Naval Academy (2 ECTS)
CSDP – coordinator: Romanian Naval Academy (2 ECTS)
Gender Perspectives in Naval Forces – coordinator: Polish Naval Academy (2 ECTS)
WP3 - Course resources will be harmonized in the project framework – responsible partners:

## Slide 20
Team members for HASS courses’ development:
COURSES | RNA team members | NVNA team members | PNA team members | INA team members
Naval Leadership (INA) | Popa Cătălin catalin.popa@anmb.ro | Valeri Stoyanov v.stoyanov@nvna.eu | Radosław Tyślewicz r.tyslewicz@amw.gdynia.pl | 
Maritime Security (NVNA) | Nistor Filip filip.nistor@anmb.ro | Valentin Vasilev - Leader valentin.vasilev@nvna.eu | Sławomir Kuźmicki s.kuzmicki@amw.gdynia.pl | 
CSDP (RNA) | Popa Cătălin - Leader catalin.popa@anmb.ro | Siyana Lutzkanova s.lutzkanova@nvna.eu | Monika Wysocka mo.wysocka@amw.gdynia.pl | 
Gender Perspectives in Naval Forces (PNA) | Popa Cătălin catalin.popa@anmb.ro | Stanislava Stefanova st.stefanova@nvna.eu | Monika Wysocka - Leader mo.wysocka@amw.gdynia.pl | 

## Slide 21
TIME LINE for IMPLEMENTATION
August – December 2024 – curriculum design (syllabuses approval) - RNA
June 2024 – February 2025 – learning materials development (textbox, ppt, study cases)
June 2024 – July 2025 – platform upload, learning materials roll-on and testing
March 2025 – July 2024 – BIP development, testing the materials with the students in learning activities
ACTIVITIES TO BE ORGANIZED during WP3
TM3 – Project meeting – EU core of values curricular developments – NVNA, Varna, Bulgaria, October 2024 – 2 days, 2 pax/partner, 07- 09.10.2024;
Online groups meetings for each course organized by the leading team.
WP3 – TASKS AND RESPONSABILITIES:

## Slide 22
COURSES TO BE ORGANIZED during WP3
C5S. NHEI ESDP harmonized curriculum for developing an EU Security culture on CSDP – organized by RNA, in Romania - 1 module to be delivered residentialy: ”EU Common Security and Defence Policy” (2 ECTS) - 8 students to be instructed (2 students/partner) – 5 days, 10.03-14.03.2025;
C6S. NHEI ESDP harmonized curriculum for Maritime Security – organized by NVNA, in Bulgaria - 1 module to be delivered residentialy: ” EU Maritime Security” (2 ECTS) - 8 students to be instructed (2 students/partner) – 5 days, 14.04-18.04.2025;
C7S. NHEI ESDP harmonized curriculum for Naval Leadership on EU social and military core values– organized by INA, in Italy - 1 module to be delivered residentialy: ” Naval Leadership” (2 ECTS) - 8 students to be instructed (2 students/partner) – 5 days, 05.05-10.05.2025;
C82. NHEI EU diversity competencies - Gender Navy Perspectives seminar – organized by PNA, in Poland - 1 module to be delivered residentialy: ”Gender Issues in Naval Forces” (2 ECTS) - 8 students to be instructed (2 students/partner) – 5 days, 09.06-13.06.2025;
WP3 – TASKS AND RESPONSABILITIES:

## Slide 23
Work package n°4 description – coordinator Romanian Naval Academy (RNA)
A.4.1. Designing and building a virtual e-campus platform (VCP) for Navy Military Higher Education network - RESULTS: 1 virtual e-campus platform (VCP) designed for Navy Military Higher Education hosted by RNA on lung term → responsible: RNA;
A4.2. Implementation of a virtual online platform for Navy Military Higher Education network – RESULTS: 12 courses uploaded as learning digital resources on the VCP and 1 digital International Naval Semester portfolio implemented among the partners → responsible: RNA;
A4.3. Transnational meetings and events – RESULTS: TPM3 Project meeting – Military EQF curriculum design and digital education (RNA, Romania), TPM4 Project meeting – strategies of INS implementation (INA, Italy); Public event E2: HASS curriculum development in Navy Military Higher Education (INA, Italy), Public event 3 – closure conference – International Naval
Semester implementation - challenges and rewards (PNA, Poland).

## Slide 24
Work package n°4 timeline – coordinator Romanian Naval Academy

## Slide 25
TIME LINE for IMPLEMENTATION
March 2024 – May 2024 – Designing and building a virtual e-campus platform (VCP) for Navy Military Higher Education network - RNA;
December 2024 – May 2024 – platform upload, e-campus operational - RNA;
ACTIVITIES TO BE ORGANIZED during WP4
TM4 – Project meeting – online meeting – ”Military EQF curriculum design and digital education” – RNA online, June 2024 – 1 day, 2 pax/partner, 11.06.2024;
TM5 – Project meeting –” Strategies of INS implementation” – INA, in Italy, June 2024 – 3 days, 2 pax/partner, 09.06-12.06.2024;
E2 Public event: HASS curriculum development in Navy Military Higher Education - awareness campaign on EU culture and values – organized by INA, in Italy – 1 day, 30 participants, May 2025;
E3 Public event: Public event 3 – closure conference – International Naval Semester implementation -challenges and rewards – organized by PNA, in Poland – 1 day, 30 participants, July 2025.
WP4 – TASKS AND RESPONSABILITIES:

## Slide 26
TASK TO FOLLOW!
ADMINISTRATIVE TASKS
Concluding the signature of the financial contracts – deadline: 20.02.2024 (INA);
Open the project management portal (marplat.eu) – https://marplat.eu/course/view.php?id=62;
Design the project website – https://www.anmb.ro/navy-ins-tech;
Build the project roll-up and the project leaflet – deadline: 28.02.2024 (RNA);
Prepare the format documents (time sheet., events docs, etc) – deadline: 01.03.2024;
Organize the 1st Event in Romania – 17.05.2024 (SeaConf 2024);
PROJECT IMPLEMENTATION - ACADEMIC TASKS
Establish the project teams: project coordinator, administrative responsible, academic coordinator, team members in the course development groups – deadline: 15.02.2024 (all partners);
Each partner will establish the period for 2023: C1S, C2S, C3S, C4S, TM2 and TM3 – deadline: 15.02.2024 (all partners)
Proposal for course format: textbox, seminar format, labs tutorials – deadline: 01.03.2024 (all partners);

## Slide 27
QUESTIONS?
Thank you for your kind attention!